## M1 - M1 Project Estimation
Title | URL | Assignees | Status | Linked pull requests | Time Estimate | Coding Time | Non-Coding Time | Sub-issues progress
Create navbar for landing page | https://github.com/RI-Bows/RIBows/issues/3 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/22
Upload Project to Vercel | https://github.com/RI-Bows/RIBows/issues/6 | g3rr1c | Done |  | 3 | 3 | 2
Create mockup of login page | https://github.com/RI-Bows/RIBows/issues/9 | ethnchiu | Done
Determine design for hero page | https://github.com/RI-Bows/RIBows/issues/4 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/34
Updating project home page (M1) | https://github.com/RI-Bows/RIBows/issues/5 | KateHamada | Done | https://github.com/RI-Bows/ri-bows.github.io/pull/16
Create a mockup of add RIO page | https://github.com/RI-Bows/RIBows/issues/13 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/27 | 1 | 2 | 0
Create a footer for landing page | https://github.com/RI-Bows/RIBows/issues/18 | g3rr1c | Done | https://github.com/RI-Bows/RIBows/pull/41 | 2 | 1 | 1
Add interests to sign-in page | https://github.com/RI-Bows/RIBows/issues/25 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/26
Create database | https://github.com/RI-Bows/RIBows/issues/1 | cbxiii | Done | https://github.com/RI-Bows/RIBows/pull/39 | 5 | 2 | 3
Add pictures to Hero Page | https://github.com/RI-Bows/RIBows/issues/17 | tjlacasio | Done |  | 1 | 1 | 0
Create mockup of edit profile page | https://github.com/RI-Bows/RIBows/issues/16 | cbxiii | Done | https://github.com/RI-Bows/RIBows/pull/40
Create a mockup of bookmarks page | https://github.com/RI-Bows/RIBows/issues/2 | cbxiii | Done | https://github.com/RI-Bows/RIBows/pull/24
Create mockup of sign up page | https://github.com/RI-Bows/RIBows/issues/20 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/21
Update Navbar | https://github.com/RI-Bows/RIBows/issues/32 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/33
Create feedback form | https://github.com/RI-Bows/RIBows/issues/43 | g3rr1c | Done |  | 2 | 1.75 | 0.25
Interface with UH Mānoa Approved RIOs Google Spreadsheet and parse RIO data | https://github.com/RI-Bows/RIBows/issues/36 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/45
Fix landing page pictures | https://github.com/RI-Bows/RIBows/issues/48 | g3rr1c | Done |  | 1 | 0.75 | 0.25
Title | URL | Assignees | Status | Linked pull requests | Sub-issues progress | Time Estimate | Coding Time | Non-coding Time
Create Feedback page/ Form | https://github.com/RI-Bows/RIBows/issues/31 | cbxiii | Done | https://github.com/RI-Bows/RIBows/pull/92 |  | 2 | 1 | 1
Create an About Us page/Info page | https://github.com/RI-Bows/RIBows/issues/54 | cbxiii | Done | https://github.com/RI-Bows/RIBows/pull/63 |  | 1 | 2 | 1
Improve sign up error handling | https://github.com/RI-Bows/RIBows/issues/68 | cbxiii | Done | https://github.com/RI-Bows/RIBows/pull/93 |  | 2 | 1 | 1
Link sign up page to database | https://github.com/RI-Bows/RIBows/issues/58 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/59 |  | 1 | 1 | 0.5
Fix search page alphabetical filter | https://github.com/RI-Bows/RIBows/issues/107 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/108 |  | 0.5 | 0.5 | 0
Link Search bar to database | https://github.com/RI-Bows/RIBows/issues/50 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/106 |  | 1 | 1 | 0
Remove unused schema models | https://github.com/RI-Bows/RIBows/issues/69 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/84 |  | 0.5 | 1 | 0.5
Update prisma schema to include bookmarks counter | https://github.com/RI-Bows/RIBows/issues/82 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/83 |  | 0.5 | 0.5 | 0
Create cron job to periodically update RIO data from spreadsheet | https://github.com/RI-Bows/RIBows/issues/46 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/80 |  | 1 | 0.5 | 0
Fix spreadsheet syncing | https://github.com/RI-Bows/RIBows/issues/78 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/79 |  | 0.5 | 0.5 | 0
Fix sign up page interests multiselect dropdown | https://github.com/RI-Bows/RIBows/issues/61 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/70 |  | 0.5 | 1 | 0.5
Restyle sign in and sign up pages | https://github.com/RI-Bows/RIBows/issues/71 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/72 |  | 0.5 | 1 | 0
Create CI badge on project home page | https://github.com/RI-Bows/RIBows/issues/57 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/85 |  | 0.5 | 1 | 0.5
change search bar filters to multiple rows | https://github.com/RI-Bows/RIBows/issues/111 | g3rr1c | Done | https://github.com/RI-Bows/RIBows/pull/112 |  | 0.5 | 0.5
Create a mockup of Search tab | https://github.com/RI-Bows/RIBows/issues/37 | g3rr1c | Done |  |  | 3 | 4 | 2
Create RiO pop up card | https://github.com/RI-Bows/RIBows/issues/75 | g3rr1c | Done | https://github.com/RI-Bows/RIBows/pull/105 |  | 4 | 2 | 2
Fix search bar logic | https://github.com/RI-Bows/RIBows/issues/101 | g3rr1c | Done |  |  | 0.5 | 0.5
Connect edit RIO page to database | https://github.com/RI-Bows/RIBows/issues/14 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/64 |  | 2 | 3 | 0
Implement Playwright “availability” tests for all pages. | https://github.com/RI-Bows/RIBows/issues/42 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/94, https://github.com/RI-Bows/RIBows/pull/95 |  | 2 | 3 | 0
Get EditClub page to update database | https://github.com/RI-Bows/RIBows/issues/65 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/66 |  | 2 | 1.5 | 0
Create Club Account | https://github.com/RI-Bows/RIBows/issues/96 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/97 |  | 1 | 0.75 | 0
Add Continuous Integration Section to github.io page | https://github.com/RI-Bows/RIBows/issues/98 | KateHamada | Done | https://github.com/RI-Bows/ri-bows.github.io/pull/19 |  | 1 | 1 | 0
Fix ESLint error & Playwright Test Error | https://github.com/RI-Bows/RIBows/issues/99 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/100 |  | 0.5 | 0.5 | 0
Updating project home page (M2) | https://github.com/RI-Bows/ri-bows.github.io/issues/15 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/73 |  | 1 | 0.5 | 0.3
FIx styling issues | https://github.com/RI-Bows/RIBows/issues/81 | tjlacasio | Done |  |  | 1 | 1 | 0
Choose site theme | https://github.com/RI-Bows/RIBows/issues/55 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/73 |  | 2 | 3 | 0.2
Create logic for trending tab Pt.1 | https://github.com/RI-Bows/RIBows/issues/53 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/56 |  | 2 | 2.5 | 1
Title | URL | Assignees | Status | Linked pull requests | Sub-issues progress | Time Estimate | Coding Time | Non-Coding Time
Link Edit Profile to Database | https://github.com/RI-Bows/RIBows/issues/114 | cbxiii | Done | https://github.com/RI-Bows/RIBows/pull/160 |  | 0.5 | 0.5 | 0
Update Model Card Aesthetics | https://github.com/RI-Bows/RIBows/issues/140 | cbxiii | Done | https://github.com/RI-Bows/RIBows/pull/167 |  | 2 | 2 | 1
Replace all instances of the word "club" with "RIO" | https://github.com/RI-Bows/RIBows/issues/192 | cbxiii | Done | https://github.com/RI-Bows/RIBows/pull/193 |  | 0.5 | 0.5 | 0
Update schema to map saved RIOs to each user | https://github.com/RI-Bows/RIBows/issues/120 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/123 |  | 0.5 | 0.5 | 0
Restyle about us | https://github.com/RI-Bows/RIBows/issues/155 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/198 |  | 0.5 | 0.5 | 0
Restyle feedback | https://github.com/RI-Bows/RIBows/issues/156 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/195 |  | 0.5 | 0.5 | 0
Restyle footer | https://github.com/RI-Bows/RIBows/issues/154 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/194 |  | 0.5 | 0.5 | 0
Fix home page search bar shifting | https://github.com/RI-Bows/RIBows/issues/163 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/169 |  | 0.5 | 1 | 0
Implement trending logic on home page | https://github.com/RI-Bows/RIBows/issues/138 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/145 |  | 0.5 | 0.5 | 0
Add icon for search and about us in navbar | https://github.com/RI-Bows/RIBows/issues/153 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/159 |  | 0.5 | 0.5 | 0
Link Bookmarks to Database | https://github.com/RI-Bows/RIBows/issues/116 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/125 |  | 1 | 1 | 0.5
Update color scheme | https://github.com/RI-Bows/RIBows/issues/150 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/152 |  | 2 | 3 | 1
Restyle home page | https://github.com/RI-Bows/RIBows/issues/148 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/152 |  | 0.5 | 0.5 | 0
Increment bookmarks counter when adding bookmark | https://github.com/RI-Bows/RIBows/issues/134 | g3rr1c | Done | https://github.com/RI-Bows/RIBows/pull/172 |  | 2 | 4 | 1
Fix feedback page spacing | https://github.com/RI-Bows/RIBows/issues/187 | g3rr1c | Done | https://github.com/RI-Bows/RIBows/pull/188 |  | 0.25 | 0.25 | 0
Fix searchbar filter styling | https://github.com/RI-Bows/RIBows/issues/174 | g3rr1c | Done | https://github.com/RI-Bows/RIBows/pull/181 |  | 0.25 | 0.25 | 0
Fix search cards styling | https://github.com/RI-Bows/RIBows/issues/118 | g3rr1c | Done | https://github.com/RI-Bows/RIBows/pull/124 |  | 0.5 | 0.5 | 0
Fix bookmark counter again | https://github.com/RI-Bows/RIBows/issues/182 | g3rr1c | Done | https://github.com/RI-Bows/RIBows/pull/183 |  | 1 | 1 | 0
Fix card spacing for bookmark tab | https://github.com/RI-Bows/RIBows/issues/141 | g3rr1c | Done | https://github.com/RI-Bows/RIBows/pull/143 |  | 0.25 | 0.25 | 0
Implement bookmark button to RIO card | https://github.com/RI-Bows/RIBows/issues/110 | g3rr1c | Done | https://github.com/RI-Bows/RIBows/pull/130 |  | 4 | 3 | 2
Create EditClub page for admin | https://github.com/RI-Bows/RIBows/issues/67 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/126, https://github.com/RI-Bows/RIBows/pull/131 |  | 3 | 3 | 0
Link Add RIO to Database | https://github.com/RI-Bows/RIBows/issues/115 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/157 |  | 2.5 | 3 | 0
Fix Github Playwright Error | https://github.com/RI-Bows/RIBows/issues/132 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/178, https://github.com/RI-Bows/RIBows/pull/199, https://github.com/RI-Bows/RIBows/pull/200 |  | 3 | 3 | 2
Update github.io home page | https://github.com/RI-Bows/RIBows/issues/133 | KateHamada | Done | https://github.com/RI-Bows/ri-bows.github.io/pull/20 |  | 1 | 0.75 | 0.25
Add Delete button for admin | https://github.com/RI-Bows/RIBows/issues/135 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/175 |  | 3 | 1.5 | 0
Update Navbar | https://github.com/RI-Bows/RIBows/issues/142 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/158 |  | 0.5 | 0.5 | 0
Ensure consistent padding and margins across all pages | https://github.com/RI-Bows/RIBows/issues/151 | tjlacasio | Done
Update Help Page to current style | https://github.com/RI-Bows/RIBows/issues/196 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/197 |  | 0.5 | 0.5 | 0
Fix google form | https://github.com/RI-Bows/RIBows/issues/185 | tjlacasio | Done |  |  | 0.5 | 0 | 0.5
Make bookmark button clickable in RIO card | https://github.com/RI-Bows/RIBows/issues/177 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/180 |  | 0.5 | 1 | 0
update landing search bar to have updated card | https://github.com/RI-Bows/RIBows/issues/171 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/173 |  | 1 | 1 | 0
Check and fix all buttons across the site | https://github.com/RI-Bows/RIBows/issues/164 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/170 |  | 1 | 1 | 0
Fix bookmarks view | https://github.com/RI-Bows/RIBows/issues/121 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/129 |  | 0.5 | 0.5 | 0
Fix styling | https://github.com/RI-Bows/RIBows/issues/119 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/146 |  | 1 | 1 | 0
Add Search bar Feature to Landing Page | https://github.com/RI-Bows/RIBows/issues/137 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/161 |  | 2 | 3 | 0
Add image to RIO cards | https://github.com/RI-Bows/RIBows/issues/186 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/190 |  | 1 | 1.5 | 0
Fix sign in page error handling | https://github.com/RI-Bows/RIBows/issues/122 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/166 |  | 1 | 1 | 0
Create help/guide page that provides instructions on how to use the site | https://github.com/RI-Bows/RIBows/issues/144 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/162 |  | 1 | 1 | 0

## Members Total
Team Member | Total development experience for each team member (months) | How was coding effort tracked? | How was non-coding effort tracked
Ethan | 12 | Timer/Best Guess | Best Guess
Kate | 5 | Timer/ Best Guess | Best Guess
Gerric | 5 | Timer/ Best Guess | Best Guess
Charles
TJ | 14 | Best Guess | Best Guess

## Charles
Title | URL | Assignees | Status | Linked pull requests | Time Estimate | Coding Time | Non-Coding Time | Sub-issues progress | Time Estimate | Coding Time | Non-Coding Time
Create database | https://github.com/RI-Bows/RIBows/issues/1 | cbxiii | Done | https://github.com/RI-Bows/RIBows/pull/39 | 5 | 2 | 3 |  | 13 | 9 | 7
Create mockup of edit profile page | https://github.com/RI-Bows/RIBows/issues/16 | cbxiii | Done | https://github.com/RI-Bows/RIBows/pull/40
Create a mockup of bookmarks page | https://github.com/RI-Bows/RIBows/issues/2 | cbxiii | Done | https://github.com/RI-Bows/RIBows/pull/24
Title | URL | Assignees | Status | Linked pull requests | Sub-issues progress | Time Estimate | Coding Time | Non-coding Time
Create Feedback page/ Form | https://github.com/RI-Bows/RIBows/issues/31 | cbxiii | Done | https://github.com/RI-Bows/RIBows/pull/92 |  | 2 | 1 | 1
Create an About Us page/Info page | https://github.com/RI-Bows/RIBows/issues/54 | cbxiii | Done | https://github.com/RI-Bows/RIBows/pull/63 |  | 1 | 2 | 1
Improve sign up error handling | https://github.com/RI-Bows/RIBows/issues/68 | cbxiii | Done | https://github.com/RI-Bows/RIBows/pull/93 |  | 2 | 1 | 1
Title | URL | Assignees | Status | Linked pull requests | Sub-issues progress | Time Estimate | Coding Time | Non-Coding Time
Link Edit Profile to Database | https://github.com/RI-Bows/RIBows/issues/114 | cbxiii | Done | https://github.com/RI-Bows/RIBows/pull/160 |  | 0.5 | 0.5 | 0
Update Model Card Aesthetics | https://github.com/RI-Bows/RIBows/issues/140 | cbxiii | Done | https://github.com/RI-Bows/RIBows/pull/167 |  | 2 | 2 | 1
Replace all instances of the word "club" with "RIO" | https://github.com/RI-Bows/RIBows/issues/192 | cbxiii | Done | https://github.com/RI-Bows/RIBows/pull/193 |  | 0.5 | 0.5 | 0

## Kate
Title | URL | Assignees | Status | Linked pull requests | Time Estimate | Coding Time | Non-Coding Time | Time Estimate | Coding Time | Non-Coding Time
Update Navbar | https://github.com/RI-Bows/RIBows/issues/32 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/33 |  |  |  | 21.5 | 21.5 | 2.25
Create navbar for landing page | https://github.com/RI-Bows/RIBows/issues/3 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/22
Determine design for hero page | https://github.com/RI-Bows/RIBows/issues/4 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/34
Updating project home page (M1) | https://github.com/RI-Bows/RIBows/issues/5 | KateHamada | Done | https://github.com/RI-Bows/ri-bows.github.io/pull/16
Title | URL | Assignees | Status | Linked pull requests | Time Estimate | Coding Time | Non-coding Time
Connect edit RIO page to database | https://github.com/RI-Bows/RIBows/issues/14 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/64 | 2 | 3 | 0
Implement Playwright “availability” tests for all pages. | https://github.com/RI-Bows/RIBows/issues/42 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/94, https://github.com/RI-Bows/RIBows/pull/95 | 2 | 3 | 0
Get EditClub page to update database | https://github.com/RI-Bows/RIBows/issues/65 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/66 | 2 | 1.5 | 0
Create Club Account | https://github.com/RI-Bows/RIBows/issues/96 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/97 | 1 | 0.75 | 0
Add Continuous Integration Section to github.io page | https://github.com/RI-Bows/RIBows/issues/98 | KateHamada | Done | https://github.com/RI-Bows/ri-bows.github.io/pull/19 | 1 | 1 | 0
Fix ESLint error & Playwright Test Error | https://github.com/RI-Bows/RIBows/issues/99 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/100 | 0.5 | 0.5 | 0
Title | URL | Assignees | Status | Linked pull requests | Time Estimate | Coding Time | Non-Coding Time
Create EditClub page for admin | https://github.com/RI-Bows/RIBows/issues/67 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/126, https://github.com/RI-Bows/RIBows/pull/131 | 3 | 3 | 0
Link Add RIO to Database | https://github.com/RI-Bows/RIBows/issues/115 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/157 | 2.5 | 3 | 0
Fix Github Playwright Error | https://github.com/RI-Bows/RIBows/issues/132 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/178, https://github.com/RI-Bows/RIBows/pull/199, https://github.com/RI-Bows/RIBows/pull/200 | 3 | 3 | 2
Update github.io home page | https://github.com/RI-Bows/RIBows/issues/133 | KateHamada | Done | https://github.com/RI-Bows/ri-bows.github.io/pull/20 | 1 | 0.75 | 0.25
Add Delete button for admin | https://github.com/RI-Bows/RIBows/issues/135 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/175 | 3 | 1.5 | 0
Update Navbar | https://github.com/RI-Bows/RIBows/issues/142 | KateHamada | Done | https://github.com/RI-Bows/RIBows/pull/158 | 0.5 | 0.5 | 0

## Gerric
Title | URL | Assignees | Status | Linked pull requests | Time Estimate | Coding Time | Non-Coding Time | Time Estimate | Coding Time | Non-Coding Time
Upload Project to Vercel | https://github.com/RI-Bows/RIBows/issues/6 | g3rr1c | Done |  | 3 | 1 | 2 | 23.25 | 20.75 | 9.5
Create a footer for landing page | https://github.com/RI-Bows/RIBows/issues/18 | g3rr1c | Done | https://github.com/RI-Bows/RIBows/pull/41 | 1 | 1 | 0
Create feedback form | https://github.com/RI-Bows/RIBows/issues/43 | g3rr1c | Done |  | 2 | 1.75 | 0.25
Fix landing page pictures | https://github.com/RI-Bows/RIBows/issues/48 | g3rr1c | Done |  | 1 | 0.75 | 0.25
Title | URL | Assignees | Status | Linked pull requests | Time Estimate | Coding Time | Non-coding Time
change search bar filters to multiple rows | https://github.com/RI-Bows/RIBows/issues/111 | g3rr1c | Done | https://github.com/RI-Bows/RIBows/pull/112 | 0.5 | 0.5 | 0
Create a mockup of Search tab | https://github.com/RI-Bows/RIBows/issues/37 | g3rr1c | Done |  | 3 | 4 | 2
Create RiO pop up card | https://github.com/RI-Bows/RIBows/issues/75 | g3rr1c | Done | https://github.com/RI-Bows/RIBows/pull/105 | 4 | 2 | 2
Fix search bar logic | https://github.com/RI-Bows/RIBows/issues/101 | g3rr1c | Done |  | 0.5 | 0.5 | 0
Title | URL | Assignees | Status | Linked pull requests | Time Estimate | Coding Time | Non-Coding Time
Increment bookmarks counter when adding bookmark | https://github.com/RI-Bows/RIBows/issues/134 | g3rr1c | Done | https://github.com/RI-Bows/RIBows/pull/172 | 2 | 4 | 1
Fix feedback page spacing | https://github.com/RI-Bows/RIBows/issues/187 | g3rr1c | Done | https://github.com/RI-Bows/RIBows/pull/188 | 0.25 | 0.25 | 0
Fix searchbar filter styling | https://github.com/RI-Bows/RIBows/issues/174 | g3rr1c | Done | https://github.com/RI-Bows/RIBows/pull/181 | 0.25 | 0.25 | 0
Fix search cards styling | https://github.com/RI-Bows/RIBows/issues/118 | g3rr1c | Done | https://github.com/RI-Bows/RIBows/pull/124 | 0.5 | 0.5 | 0
Fix bookmark counter again | https://github.com/RI-Bows/RIBows/issues/182 | g3rr1c | Done | https://github.com/RI-Bows/RIBows/pull/183 | 1 | 1 | 0
Fix card spacing for bookmark tab | https://github.com/RI-Bows/RIBows/issues/141 | g3rr1c | Done | https://github.com/RI-Bows/RIBows/pull/143 | 0.25 | 0.25 | 0
Implement bookmark button to RIO card | https://github.com/RI-Bows/RIBows/issues/110 | g3rr1c | Done | https://github.com/RI-Bows/RIBows/pull/130 | 4 | 3 | 2

## Ethan
Title | URL | Assignees | Status | Linked pull requests | Time Estimate | Coding Time | Non-Coding Time | Time Estimate | Coding Time | Non-Coding Time
Create mockup of login page | https://github.com/RI-Bows/RIBows/issues/9 | ethnchiu | Done |  |  |  |  | 13.5 | 16.5 | 3.5
Add interests to sign-in page | https://github.com/RI-Bows/RIBows/issues/25 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/26
Create mockup of sign up page | https://github.com/RI-Bows/RIBows/issues/20 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/21
Interface with UH Mānoa Approved RIOs Google Spreadsheet and parse RIO data | https://github.com/RI-Bows/RIBows/issues/36 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/45
Title | URL | Assignees | Status | Linked pull requests | Time Estimate | Coding Time | Non-coding Time
Link sign up page to database | https://github.com/RI-Bows/RIBows/issues/58 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/59 | 1 | 1 | 0.5
Fix search page alphabetical filter | https://github.com/RI-Bows/RIBows/issues/107 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/108 | 0.5 | 0.5 | 0
Link Search bar to database | https://github.com/RI-Bows/RIBows/issues/50 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/106 | 1 | 1 | 0
Remove unused schema models | https://github.com/RI-Bows/RIBows/issues/69 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/84 | 0.5 | 1 | 0.5
Update prisma schema to include bookmarks counter | https://github.com/RI-Bows/RIBows/issues/82 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/83 | 0.5 | 0.5 | 0
Create cron job to periodically update RIO data from spreadsheet | https://github.com/RI-Bows/RIBows/issues/46 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/80 | 1 | 0.5 | 0
Fix spreadsheet syncing | https://github.com/RI-Bows/RIBows/issues/78 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/79 | 0.5 | 0.5 | 0
Fix sign up page interests multiselect dropdown | https://github.com/RI-Bows/RIBows/issues/61 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/70 | 0.5 | 1 | 0.5
Restyle sign in and sign up pages | https://github.com/RI-Bows/RIBows/issues/71 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/72 | 0.5 | 1 | 0
Create CI badge on project home page | https://github.com/RI-Bows/RIBows/issues/57 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/85 | 0.5 | 1 | 0.5
Title | URL | Assignees | Status | Linked pull requests | Time Estimate | Coding Time | Non-Coding Time
Update schema to map saved RIOs to each user | https://github.com/RI-Bows/RIBows/issues/120 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/123 | 0.5 | 0.5 | 0
Restyle about us | https://github.com/RI-Bows/RIBows/issues/155 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/198 | 0.5 | 0.5 | 0
Restyle feedback | https://github.com/RI-Bows/RIBows/issues/156 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/195 | 0.5 | 0.5 | 0
Restyle footer | https://github.com/RI-Bows/RIBows/issues/154 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/194 | 0.5 | 0.5 | 0
Fix home page search bar shifting | https://github.com/RI-Bows/RIBows/issues/163 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/169 | 0.5 | 1 | 0
Implement trending logic on home page | https://github.com/RI-Bows/RIBows/issues/138 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/145 | 0.5 | 0.5 | 0
Add icon for search and about us in navbar | https://github.com/RI-Bows/RIBows/issues/153 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/159 | 0.5 | 0.5 | 0
Link Bookmarks to Database | https://github.com/RI-Bows/RIBows/issues/116 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/125 | 1 | 1 | 0.5
Update color scheme | https://github.com/RI-Bows/RIBows/issues/150 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/152 | 2 | 3 | 1
Restyle home page | https://github.com/RI-Bows/RIBows/issues/148 | ethnchiu | Done | https://github.com/RI-Bows/RIBows/pull/152 | 0.5 | 0.5 | 0

## TJ
Title | URL | Assignees | Status | Linked pull requests | Time Estimate | Coding Time | Non-Coding Time | Time Estimate | Coding Time | Non-Coding Time
Create a mockup of add RIO page | https://github.com/RI-Bows/RIBows/issues/13 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/27 | 1 | 2 | 0 | 18 | 21 | 2
Add pictures to Hero Page | https://github.com/RI-Bows/RIBows/issues/17 | tjlacasio | Done |  | 1 | 1 | 0
Title | URL | Assignees | Status | Linked pull requests | Time Estimate | Coding Time | Non-coding Time
Updating project home page (M2) | https://github.com/RI-Bows/ri-bows.github.io/issues/15 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/73 | 1 | 0.5 | 0.3
FIx styling issues | https://github.com/RI-Bows/RIBows/issues/81 | tjlacasio | Done |  | 1 | 1 | 0
Choose site theme | https://github.com/RI-Bows/RIBows/issues/55 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/73 | 2 | 2 | 0.2
Create logic for trending tab Pt.1 | https://github.com/RI-Bows/RIBows/issues/53 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/56 | 2 | 2.5 | 1
Title | URL | Assignees | Status | Linked pull requests | Time Estimate | Coding Time | Non-Coding Time
Ensure consistent padding and margins across all pages | https://github.com/RI-Bows/RIBows/issues/151 | tjlacasio | Done
Update Help Page to current style | https://github.com/RI-Bows/RIBows/issues/196 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/197 | 0.5 | 0.5 | 0
Fix google form | https://github.com/RI-Bows/RIBows/issues/185 | tjlacasio | Done |  | 0.5 | 0 | 0.5
Make bookmark button clickable in RIO card | https://github.com/RI-Bows/RIBows/issues/177 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/180 | 0.5 | 1 | 0
update landing search bar to have updated card | https://github.com/RI-Bows/RIBows/issues/171 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/173 | 1 | 1 | 0
Check and fix all buttons across the site | https://github.com/RI-Bows/RIBows/issues/164 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/170 | 1 | 1.5 | 0
Fix bookmarks view | https://github.com/RI-Bows/RIBows/issues/121 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/129 | 0.5 | 0.5 | 0
Fix styling | https://github.com/RI-Bows/RIBows/issues/119 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/146 | 1 | 1 | 0
Add Search bar Feature to Landing Page | https://github.com/RI-Bows/RIBows/issues/137 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/161 | 2 | 3 | 0
Add image to RIO cards | https://github.com/RI-Bows/RIBows/issues/186 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/190 | 1 | 1.5 | 0
Fix sign in page error handling | https://github.com/RI-Bows/RIBows/issues/122 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/166 | 1 | 1 | 0
Create help/guide page that provides instructions on how to use the site | https://github.com/RI-Bows/RIBows/issues/144 | tjlacasio | Done | https://github.com/RI-Bows/RIBows/pull/162 | 1 | 1 | 0